Project Status Update

21st-Clone — Component Marketplace (Component workflow)

Owner: Aditya   Date: April 24, 2026   Plan version: v2.0 (10-phase upgrade)

# Snapshot

| Overall state | On track. Engine, primitives, and ~200 variants shipped; scaling to 600+ and wiring backend. |
| --- | --- |
| Phase progress | P0–P3 complete · P4 in progress · P5A/P5B active in parallel · P6–P9 queued |
| Frontend | ~75% complete (core engine, UI primitives, pages: Detail, Dashboard, MagicChat, Publish) |
| Registry | ~200 / 600+ variants across 47 categories; batch-1 through batch-4 landed |
| Backend | Supabase + OpenAI deps installed; schema + RLS + Edge Functions not yet wired |
| Build health | TypeScript: 0 errors · Build green · QA gate script scaffolded (`npm run qa`) |

# Accomplishments this cycle

- Core engine shipped — router, Sandpack preview engine, semantic search, command palette, toast/dialog/popover primitives, pagination, and lazy-card previews.

- 47-category registry scaffold in place with batches 1–4 merged (base, expansion, heroes, backgrounds, borders, shaders, texts, premium-batch-b, announcements, style-generator).

- Four additional route surfaces stood up: ComponentDetailPage, DashboardPage, MagicChatPage, PublishPage.

- Performance groundwork: virtualized grid (react-virtual), debounced search, reduced-motion hook, service worker (`public/sw.js`), Vite precompile plugin for preview chunks.

- Design-system foundation landed: Tailwind token upgrade, canonical Lucide stroke (1.75), shared <Icon> wrapper, unified 180ms fade-in.

- Remix flow MVP: RemixModal + MagicChat page wired to OpenAI client dependency (ready for endpoint integration).

# Risks & blockers

| Risk / blocker | Impact | Mitigation |
| --- | --- | --- |
| 14-state matrix retrofit on existing ~200 variants | Without retrofit, ship gate fails ("no missing variants or states" is a hard requirement). | P5B running in parallel with P5A; one category owner per batch. |
| Backend (Supabase + Auth + AI edge fns) not yet wired | Gates Phase 8; Remix, Publish, and Dashboard pages currently have no real persistence. | Start P8 immediately after P4 bug sweep; RLS test plan drafted. |
| Bundle budget (app shell ≤ 180KB gz) | Sandpack and framer-motion can push the shell over budget if not code-split. | size-limit in CI, Sandpack chunk already lazy-loaded; audit framer usage in P4. |
| Accessibility / axe gate | Serious/critical axe violations block ship. | axe-core pass scheduled in P9; primitives audited at component level in P2. |

# What's next

Sequenced against the locked 10-phase timeline. P5A and P5B run in parallel; P9 cannot close until P0–P8 are complete.

| Phase | Focus | Key deliverables | Target week |
| --- | --- | --- | --- |
| P4 | Bug fix sweep (audit P0/P1/P2) | Close all P0/P1/P2 audit items; clear TS / lint debt; no-glyph / no-emoji rules active. | This week (wraps week 4) |
| P5A | New variant batches toward 600+ | Batches 5–8 across buttons, forms, data-display, navigation. | Weeks 4–7 (in-flight) |
| P5B | 14-state retrofit of existing ~200 variants | Hover, focus, active, disabled, loading, empty, error, RTL, dense, reduced-motion, dark, light, mobile, print. | Weeks 4–7 (parallel to P5A) |
| P6 | Premium background + icon application pass | Apply gradient-mesh / aurora / grid / noise to preview frames; normalize all icons to Lucide 1.75. | Weeks 6–7 |
| P7 | Feature parity with 21st.dev / PrimeNG | Responsive preview toggle, theme switcher, CLI-style copy, keyboard shortcuts. | Weeks 7–8 |
| P8 | Backend: Supabase schema + Auth + AI edge fns | Migrations, RLS, magic-link + GitHub OAuth, Remix endpoint, rate limits. | Weeks 8–9 |
| P9 | QA automation + ship gate | axe-core, Playwright, Lighthouse-CI, size-limit — all green. | Week 10 |

# Important points — decisions we need

- Lock P8 backend kickoff date — needs decision on Supabase project region + whether to ship magic-link alone first or magic-link + GitHub OAuth together.

- Confirm whether the Dashboard/Publish pages ship behind a feature flag in v1 or are gated until P8 backend is live.

- Assign a category owner for each of the four remaining new-variant batches (P5A).

- Decide on the bundle-budget ceiling for framer-motion; current shell trend is flirting with the 180KB gz cap.

- Confirm launch cadence after week 10 — soft launch to beta list vs. public launch.

# Ship-gate success metrics

These are the non-negotiable gates for v1 ship.

- TypeScript: 0 errors.

- Lint: 0 errors; no-glyph / no-emoji / no-placeholder-image rules active.

- Lighthouse mobile: Performance ≥ 90, Accessibility ≥ 95, Best Practices ≥ 95, SEO ≥ 90.

- axe-core: 0 serious/critical violations across the gallery.

- size-limit: app shell ≤ 180KB gz; Sandpack chunk lazy-loaded.

- Registry: ≥ 600 real variants across 47 categories, each with the 14-state matrix.

- RLS: 100% of Supabase tables protected, verified with anon / authed / owner roles.